## CYB 410 Project One Stepping
Green Thumb Risk Register
Positive Risk Response Options | Exploit | Share | Monitor | Accept | Probability/Impact | PI Score
Negative Risk Response Options | Avoid | Transfer | Mitigate | Accept | 1 | 1-3 | Low
Alternative Response Options | Contingency |  |  |  | 2 | 4-6 | Moderate
[5 empty] | 3 | 7-9 | High
Note: Colors in the heat map are conditionally formatted for your use in the template. Do not modify.
Risk | Something that has not happened but might
Issue | Something that has already happened
No longer active
Risk ID | Description | Risk Trigger | Risk Category | Probability (1-3) | Impact (1-3) | PI Score | Expected Result, No Action | Risk Response Type | Response Trigger | Response Description | Expected Impact of Response
| Description of the risk | How you know the risk is becoming an issue or has reached a point that requires action. | Group defines the types of risks (technological, financial, employee, etc.) | Group-sourced rough estimate of how likely this is to occur | Group-sourced rough estimate of how significant the impact of this risk will be if/when it becomes an issue | Probability multiplied by impact | What will happen if the risk becomes an issue and no action is taken | Decision made by group on how to respond to this risk (see above in blue) | How do you know it is time to put the response into play? | What is the response? | What do you expect will result from the response?
EXAMPLE | There is a chance that the project cost will exceed the amount that the company has budgeted for the work. | If the expected work remaining will cost more than $9,000 over budget, we will need to seek additional funding from management. | Financial | 2 | 3 |  | We will not be able to secure funding necessary to complete the project. Work may stop before MVP has been achieved. Product may never get to market and be deemed a total failure. | Mitigate | When estimated cost for MVP is within 5K of approved project total, we will begin seeking additional funding. | Meet with key stakeholders to review finished product, total spend to date, work remaining, and expected total spend. Ask for additional funding to complete work. | Given that our team has a mostly stable velocity and a proven ability to meet commitments and deliver value, we expect the answer to be yes provided the total amount of requests is less than $25K.
Ordering Supplies | There is a chance of not having access to the supplies necessary to support the nursery (including office supplies, fertilizer, additional inventory, and so on). | Supplier out of stock, website down, or internet outage | Operational | 2 | 3 | 6 | Stunted plant growth after 3 days; potential product loss | Mitigation | Nutrient levels reaching low threshold or ordering delays beyond one day | Switch to alternative online supplier or local store pickup | Reduced downtime in plant feeding schedule
Technology | There is a chance of not being able to access the the point-of-sale (POS) system or the licensing portal for regulated items (for example, pesticides and chemicals). | POS system outage, hardware failure, or power loss | Technical | 2 | 3 | 6 | Temporary loss of sales tracking and customer transaction slowdown | Mitigation | POS error messages or system unavailability | Switch to manual logging and use backup laptop | Continued transaction processing with minor delays
Physical Security | There is a chance that if physical security is not in place, the opportunity for breaking and entering occurs. | Camera outage, internet failure, or after-hours break-in | Security | 2 | 3 | 6 | Inability to monitor store and potential theft risk | Mitigation | Camera offline alerts or loss of cloud access | Utilize generator backup and inspect cameras regularly | Improved monitoring continuity
Asset Management | There is a chance of loss of quality control or loss of crop due to environmental factors or growing techniques. | Loss of plant inventory due to disease or poor tracking | Operational | 2 | 2 | 4 | Inaccurate inventory and revenue loss | Mitigation | High plant loss rates in Grow and Care system | Regular plant inspection and immediate documentation of losses | Improved inventory accuracy
Insurance | There is a chance of not having the proper insurance that would cover different situational issues related to business assets and employees. | Inadequate insurance coverage for key risks | Financial | 1 | 3 | 3 | High financial loss in disaster scenarios | Transfer | Annual policy review deadlines | Upgrade insurance policy to include critical areas | Reduced financial burden
Safety | There is a chance there could be an opportunity for mortal danger because of the nature of the business (for example, using ladders, forklifts, and pesticides). | Exposure to pesticide or heavy equipment accidents | Safety | 2 | 3 | 6 | Employee injury and OSHA violations | Mitigation | Safety violation or equipment malfunction | Use PPE, monthly safety reporting, follow OSHA guidelines | Reduced injury risk